Enterprise Community Partners, Inc.

READY TO RESPOND DISASTER STAFFING TOOLKIT

# Business Continuity Chief

# Job Action Sheet

| Action | Date | Notes | Done |
| --- | --- | --- | --- |
| Receive Command Level Meeting announcement from Incident Commander. |  |  |  |
| Read entire Job Action Packet with tools and fill gaps as needed. |  |  |  |
| Schedule Section Meetings with Team Leaders before Command Level Meetings over next three operational periods. Invite Logistics Chief to attend. |  |  |  |
| Assess adequacy of cash and reserves to cover potential repairs. |  |  |  |

Main functions include:

•	Staying current with the organization’s financial obligations.

•	Approving funds for purchases.

•	Holding meetings with the IT and Human Resources Team Leader.

•	Compiling the necessary documentation for post-disaster funding.

•	Shutting down the main business office if needed.

The Business Continuity Chief must be aware of the organization’s cash needs and insurance coverage, maintain vital business records and oversee important financial and operational matters.

96 Hours

Pre-Event

Name _______________________________  Phone _____________________ Date last revised _____________________

96 Hours

Pre-Event

| Action | Date | Notes | Done |
| --- | --- | --- | --- |
| Communicate with Team Leaders to update critical checklists and information. |  |  |  |
| Work with IT Team Leader to ensure documents listed in Vital Records Worksheet are up to date and stored on server. |  |  |  |

Enterprise Community Partners, Inc.

72 Hours

Pre-Event

| Action | Date | Notes | Done |
| --- | --- | --- | --- |
| Hold first Business Continuity Section Meeting with Human Resources and IT Team Leaders and Logistics Chief. |  |  |  |
| Attend First Command Level Meeting. |  |  |  |
| Receive photographs of vulnerable equipment from Housing Chief for post-disaster insurance and funding documentation. |  |  |  |
| Coordinate with Human Resources Team Leader to address staffing needs. |  |  |  |
| Confirm that Human Resources Team Leader has reissued policies on working from home, use of personal time, etc. |  |  |  |
| Confirm that Human Resources Team Leader has provided Disaster Related Hours and Expenses Worksheet to staff as necessary for insurance and reimbursement for damages after the disaster. |  |  |  |
| Coordinate with Logistics Chief on equipment and supply needs including availability of Payment Cards for staff. Charge and distribute Payment Cards to staff and Housing Chief as needed. |  |  |  |

Enterprise Community Partners, Inc.

48 Hours

Pre-Event

| Action | Date | Notes | Done |
| --- | --- | --- | --- |
| Hold Business Continuity Section Meeting. |  |  |  |
| Attend Command Level Meeting. |  |  |  |
| Confirm with Human Resources Team Leader that staff received information on accessing files, emails and server. |  |  |  |
| Work with Human Resources Team Leader to address staffing needs. |  |  |  |
| Confirm payroll can be covered for next two weeks and ensure payment of staff still using paper-based payroll. |  |  |  |
| Confirm bills to vendors can be paid for next two weeks. |  |  |  |
| Update Office Shutdown Checklist and begin shutting down central office. |  |  |  |
| Contact funders regarding any additional payments and disbursements. |  |  |  |

Enterprise Community Partners, Inc.

24 Hours

Pre-Event

| Action | Date | Notes | Done |
| --- | --- | --- | --- |
| Hold Business Continuity Section Meeting, via conference call if necessary. |  |  |  |
| Attend Command Level Meeting. |  |  |  |
| Identify last-minute needs and coordinate with Logistics Chief. |  |  |  |
| Coordinate with Human Resources Team Leader to address staffing needs. |  |  |  |
| Ensure office shutdown is underway and update Office Shutdown Checklist. |  |  |  |

Enterprise Community Partners, Inc.

12 Hours

Pre-Event

| Action | Date | Notes | Done |
| --- | --- | --- | --- |
| Attend Command Level Meeting. |  |  |  |
| Identify and fill gaps. |  |  |  |

Enterprise Community Partners, Inc.

EVENT/

Immediately Following Event

EVENT

Stay on Alert

| Action | Date | Notes | Done |
| --- | --- | --- | --- |
| Hold Business Continuity Section Meeting, at Emergency Operations Center or via conference call if necessary. |  |  |  |
| Attend Command Level Meeting and notify Incident Commander of problems regarding business functions, staffing availability and assignment updates. |  |  |  |
| Assess functionality of IT systems with IT Team Leader. |  |  |  |
| Communicate need for volunteers or additional staff to Human Resources Team Leader. |  |  |  |

# Immediately

# Following Event

Enterprise Community Partners, Inc.

Enterprise Community Partners, Inc.

12 Hours

Post-Event

| Action | Date | Notes | Done |
| --- | --- | --- | --- |
| Hold Business Continuity Section meeting. |  |  |  |
| Attend Command Level Meeting. |  |  |  |
| Work with Housing Chief to coordinate inspection by insurance adjusters as needed. Bring Insurance Coverage Guide and Insurance Coverage Worksheet to meeting. |  |  |  |
| As damage assessments come in, assess ability to pay for immediate repairs. |  |  |  |
| Ensure staff Payment Cards are adequately charged. |  |  |  |
| Schedule additional Business Continuity Section Meetings as needed. |  |  |  |